Mailman School of Public Health

Departmental Grants Preparation Team Responsibilities and Timeline

2-3 months prior to application due date

| Budget Analyst – BA (existing Department Administrator/Grants Manager) Responsibilities: | Research Assistant (RA) / Administrative Assistant (AA) Responsibilities: | Principal Investigator (PI) Responsibilities: |
| --- | --- | --- |
| Meets with Principal Investigator, Research Assistant/Administrative Assistant to review RFP or sponsor specific requirements and delegate responsibilities. | Meets with Principal Investigator and Budget Analyst to review RFP or sponsor specific requirements and delegate responsibilities. | Meets with Budget Analyst and Research Assistant/Administrative Assistant to review RFP or sponsor specific requirements and delegate responsibilities |
| Meets with the Principal Investigator to create preliminary budget. | Creates timeline for grant preparation and submission. | Provide list of investigators, consultants, collaborators and subcontracts. |
| Contact different departments to obtain accurate salary information and research costs, etc. | Performs literature searches, as needed. | Meets with the Budget Analyst to create preliminary budget |
| Responsible of obtaining a copy of agency’s written policy on overhead costs if the grant application is non-government. | Maintains the database of literature citations and ensure reference consistency and accuracy. | Responsible of writing the science. |
|  | Assist in producing drafts of the text of the “science section” including general formatting, tables and graphs, monitors length per guidelines, etc. |  |
|  | Contact appropriate investigators and consultants to request materials |  |
|  | Contact sub-contract institutions to begin paperwork, if needed. |  |
|  | Create tables and graphs for grants as needed. |  |

1-2 months prior to due date

| Budget Analyst – BA (existing Department Administrator/Grants Manager) Responsibilities: | Research Assistant (RA) / Administrative Assistant (AA) Responsibilities: | Principal Investigator (PI) Responsibilities: |
| --- | --- | --- |
| Responsible for generating the in-kind, new hire and salary increase letters and obtaining internal approval. | Continue to contact appropriate investigators to request materials: Biographical Sketches and Other Support pages ensuring consistency, accuracy and formatting. Collects documents and letters from different department both inside and outside the University. | Meets with Budget Analyst regularly to revise budget. |
| Meets with the Principal Investigator regularly to revise budget. | Assist in drafting Resources page, collect boilerplate language regarding existing resources and maintains a list of appendices while collecting appendix materials. | Regularly and frequently work with the Research Assistant/Administrative Assistant to revise the science, format, incorporate investigators revisions, etc. |
| Responsible for completion of the F & A Analysis Tool and obtaining internal approvals. | Regularly and frequently work with the Principal Investigators to revise the science, format, incorporate investigators revisions, etc. | Works with the Research Assistant/Administrative Assistant to create list of appendices and collects appendix materials. |
| Responsible for ensuring adherence to the sponsor and University policies and procedures. | Coordinates communication between investigators and ensures that all parties are working with most up-to-date information. |  |
| Facilitates communication with Office of Sponsored Projects Administration and other institutions regarding guidelines, deadlines, etc. | Updates timelines as needed |  |
| Regularly monitors progress of all aspects of grant preparation. | Maintains communication with all parties to ensure compliance to timeline. |  |
| Ensures adherence to the sponsor and University policies and procedures. |  |  |

2-4 weeks prior to application deadline

| Budget Analyst – BA (existing Department Administrator/Grants Manager) Responsibilities: | Research Assistant (RA) / Administrative Assistant (AA) Responsibilities: | Principal Investigator (PI) Responsibilities: |
| --- | --- | --- |
| Finalizes budget, assist in drafting budget justification and ensure budget justification matches final budget. | Coordinates communication between investigators to ensure compliance to timeline and ensure that all parties are working with most up-to-date information. | Regularly and frequently work with the Research Assistant/Administrative Assistant to revise the science, format, incorporate investigators revisions, etc. |
| Coordinates with RA/AA the collection of all materials needed for institutional review. | Create a RASCAL Protrack Form and obtain appropriate internal approvals with assistance from the BA. |  |
| Regularly monitors progress of all aspects of grant preparation. | Check for compliance (Conflict of Interest, HIPAA and GCP) with assistant from the BA. |  |
| Finalize all grant documents with assistance of RA/AA. | Assist in the completion of application forms. |  |
|  | Meets with the Budget Analyst to review checklist of documents and progress to date. |  |
|  | Responsible for overall grant formatting in order to adhere to RFP specifications. |  |
|  | Responsible for uploading final documents into electronic system as they are completed. |  |
|  | Updates timelines as needed |  |
|  | Assists in collecting documents, letters, from different department both inside and outside the University. |  |
|  | Finalize all grant documents with assistance from the BA |  |

7 business days prior to due date:

| Budget Analyst – BA (existing Department Administrator/Grants Manager) Responsibilities: | Research Assistant (RA) / Administrative Assistant (AA) Responsibilities: | Principal Investigator (PI) Responsibilities: |
| --- | --- | --- |
| Submits the first copy of the application to the Office of Sponsored Projects Administration (SPA) for review. | Communicates and works with the BA and PI on addressing comments provided by SPA. | Communicates and works with the BA and RA/AA on addressing comments provided by SPA |
| Responsible for communicating and working with the RA/AA and PI on addressing comments provided by SPA. |  |  |
| Responsible for ensuring that all of SPA’s comments are addressed prior to sending final version to SPA for final review and approval. |  |  |

3 business days prior to due date:

| Budget Analyst – BA (existing Department Administrator/Grants Manager) Responsibilities: | Research Assistant (RA) / Administrative Assistant (AA) Responsibilities: | Principal Investigator (PI) Responsibilities: |
| --- | --- | --- |
|  | Finalize all grant documents. Printing and paginating of final grant documents. Grant duplication and collation. Binding, packaging and shipping of final proposal. |  |
| Application is on its way to the sponsor. |